## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Anamika Sharma | 2026-01-15 | st.pie_chart causes error on Admin dashboard. | Sprint 4 | Anamika Sharma | UI/UX | Replaced with st.bar_chart for stable rendering. | 2026-01-15 | Closed | Library compatibility issue with specific data types in Streamlit.
2 | Anamika Sharma | 2026-01-16 | FAQ section cluttering the login and submission pages. | Sprint 3 | Anamika Sharma | UI/UX | Moved FAQ to a dedicated help_support.py page. | 2026-01-16 | Closed | Ul refactor to reduce cognitive load and improve user experience.
3 | Anamika Sharma | 2026-01-18 | Tickets disappearing after browser refresh or server restart. | Sprint 4 | Anamika Sharma | Database | Implemented SQLite persistence via database.py. | 2026-01-18 | Closed | Transitioned from volatile session state to persistent disk storage.
4 | Anamika Sharma | 2026-01-20 | Model outputting "Standard" instead of the required "High" label. | Sprint 4 | Anamika Sharma | ML Engine | Added mapping logic in engine_wrapper.py to normalize labels. | 2026-01-20 | Closed | Discrepancy between model class output and business priority labels.
5 | Anamika Sharma | 2026-01-21 | 502 Bad Gateway error on Render due to heavy model load. | Deployment | Anamika Sharma | Infrastructure | Optimized RAM in requirements.txt and confirmed port binding. | 2026-01-21 | Closed | Memory leak caused by loading full BERT instead of DistilBERT-CPU.
6 | Anamika Sharma | 2026-01-21 | SLA timer showing incorrect age for newly created tickets. | Sprint 4 | Anamika Sharma | Logic | Refactored datetime.now() delta calculation in the backend. | 2026-01-21 | Closed | Timezone mismatch between server clock and local timestamp.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others